## Master Tracker
SOC DOCUMENTATION BUILD TRACKER — L1 & L2 READINESS
Trellix · Wazuh · Teramind · FortiMail · FortiGate · Cloudflare / Medianova / FortiWeb · Elastic · Nessus · Velociraptor
Doc ID | Wave | Type | Level | Title | Tool / Area | Priority | Build Days | Due (Target) | Assigned To | Status | % Complete | Date Started | Date Completed | Reviewed By | Notes / GLPI #
Wave 1 — SOPs (Governance Foundation)
SOP-001 | Wave 1 | SOP | Both | SOC Daily Operations & Shift Handover | All | P1 | 3 | Week 1 |  | Not Started | 0
SOP-002 | Wave 1 | SOP | Both | Alert Triage & Severity Classification | Elastic / All | P1 | 3 | Week 1 |  | Not Started | 0
SOP-003 | Wave 1 | SOP | Both | GLPI Ticket Lifecycle (Open to Processing to Solved) | GLPI | P1 | 2 | Week 1 |  | Not Started | 0
SOP-004 | Wave 1 | SOP | Both | Incident Escalation & Communication (L1 > L2 > HOIT) | All | P1 | 3 | Week 2 |  | Not Started | 0
SOP-005 | Wave 1 | SOP | L2 | Evidence Collection & Chain of Custody | Velociraptor / All | P1 | 3 | Week 2 |  | Not Started | 0
SOP-006 | Wave 1 | SOP | Both | Vulnerability Management & Remediation Tracking | Nessus | P1 | 3 | Week 2 |  | Not Started | 0
SOP-007 | Wave 1 | SOP | L2 | Log Management, Retention & Elastic SIEM Health | Elastic | P2 | 3 | Week 3 |  | Not Started | 0
SOP-008 | Wave 1 | SOP | L2 | User Behavior Monitoring & Insider Threat Governance | Teramind | P2 | 2 | Week 3 |  | Not Started | 0
SOP-009 | Wave 1 | SOP | L2 | Endpoint Protection Policy & EDR Management | Trellix / Wazuh | P2 | 3 | Week 3 |  | Not Started | 0
SOP-010 | Wave 1 | SOP | Both | New SOC Analyst Onboarding & Tool Access | All | P2 | 2 | Week 4 |  | Not Started | 0
SOP-011 | Wave 1 | SOP | Both | Post-Incident Review & Lessons Learned | All | P2 | 2 | Week 4 |  | Not Started | 0
SOP-012 | Wave 1 | SOP | L2 | Threat Intelligence Consumption & IOC Management | Elastic / All | P3 | 3 | Week 5 |  | Not Started | 0
Wave 2 — Daily Operations Playbooks
PB-001 | Wave 2 | PB | L1 | Morning Shift Startup & Alert Queue Review | Elastic | P1 | 1 | Week 1 |  | Not Started | 0
PB-002 | Wave 2 | PB | L1 | Elastic SIEM — Alert Triage & Initial Classification | Elastic | P1 | 2 | Week 1 |  | Not Started | 0
PB-003 | Wave 2 | PB | Both | Shift Handover Checklist & Ticket Status Sync | GLPI / Elastic | P1 | 1 | Week 1 |  | Not Started | 0
PB-004 | Wave 2 | PB | L1 | GLPI Ticket Creation from Elastic Alert (manual) | GLPI / Elastic | P1 | 1 | Week 2 |  | Not Started | 0
PB-005 | Wave 2 | PB | L2 | Weekly Nessus Scan Execution & Report Review | Nessus | P1 | 2 | Week 2 |  | Not Started | 0
PB-006 | Wave 2 | PB | L2 | Critical/High Vulnerability Triage & Owner Assignment | Nessus | P1 | 2 | Week 2 |  | Not Started | 0
PB-007 | Wave 2 | PB | L1 | Wazuh Agent Health Check & Offline Agent Response | Wazuh | P1 | 1 | Week 2 |  | Not Started | 0
PB-008 | Wave 2 | PB | L1 | Trellix Console Daily Review & Alert Disposition | Trellix | P1 | 2 | Week 2 |  | Not Started | 0
PB-009 | Wave 2 | PB | L1 | FortiGate Firewall Log Review (Daily Checks) | FortiGate | P2 | 1 | Week 3 |  | Not Started | 0
PB-010 | Wave 2 | PB | L1 | FortiMail Daily Queue & Quarantine Review | FortiMail | P2 | 1 | Week 3 |  | Not Started | 0
Wave 3 — Endpoint & Malware Playbooks
PB-011 | Wave 3 | PB | L1/L2 | Malware Detection — Trellix Alert Triage & Containment | Trellix | P1 | 2 | Week 2 |  | Not Started | 0
PB-012 | Wave 3 | PB | L2 | Ransomware Suspected — Isolation & Escalation | Trellix / Wazuh | P1 | 3 | Week 2 |  | Not Started | 0
PB-013 | Wave 3 | PB | L1/L2 | Suspicious Process Execution on Windows Endpoint | Trellix / Wazuh | P1 | 2 | Week 3 |  | Not Started | 0
PB-014 | Wave 3 | PB | L1 | File Integrity Monitoring (FIM) Alert — Wazuh | Wazuh | P2 | 2 | Week 3 |  | Not Started | 0
PB-015 | Wave 3 | PB | L2 | Rootkit / Kernel-Level Detection — Wazuh | Wazuh | P2 | 2 | Week 3 |  | Not Started | 0
PB-016 | Wave 3 | PB | L1/L2 | Brute Force Attack — Windows (RDP/SMB) | Wazuh / Elastic | P1 | 2 | Week 2 |  | Not Started | 0
PB-017 | Wave 3 | PB | L1/L2 | Brute Force Attack — Linux (SSH) | Wazuh / Elastic | P1 | 2 | Week 2 |  | Not Started | 0
PB-018 | Wave 3 | PB | L2 | Privilege Escalation Detected — Windows or Linux | Wazuh / Trellix | P1 | 2 | Week 3 |  | Not Started | 0
PB-019 | Wave 3 | PB | L2 | Lateral Movement Detected (Pass-the-Hash / WMI / RDP) | Elastic / Wazuh | P1 | 3 | Week 3 |  | Not Started | 0
PB-020 | Wave 3 | PB | L2 | Velociraptor — Endpoint Forensic Collection | Velociraptor | P2 | 2 | Week 4 |  | Not Started | 0
PB-021 | Wave 3 | PB | L2 | Velociraptor — Threat Hunt Execution (targeted IOC) | Velociraptor | P2 | 2 | Week 4 |  | Not Started | 0
Wave 4 — Network & Perimeter Playbooks
PB-022 | Wave 4 | PB | L1 | Firewall Policy Violation / Unauthorized Access Attempt | FortiGate | P2 | 2 | Week 3 |  | Not Started | 0
PB-023 | Wave 4 | PB | L2 | Suspicious Outbound Traffic / C2 Beaconing | FortiGate / Elastic | P1 | 2 | Week 3 |  | Not Started | 0
PB-024 | Wave 4 | PB | L2 | DDoS Detection & Mitigation (volumetric) | FortiGate / Cloudflare | P2 | 3 | Week 4 |  | Not Started | 0
PB-025 | Wave 4 | PB | L1/L2 | WAF Alert — SQL Injection Attempt | FortiWeb / Cloudflare | P2 | 2 | Week 4 |  | Not Started | 0
PB-026 | Wave 4 | PB | L1/L2 | WAF Alert — XSS / Code Injection Attempt | FortiWeb / Cloudflare | P2 | 2 | Week 4 |  | Not Started | 0
PB-027 | Wave 4 | PB | L1 | Bot / Scraping Attack Detected | Cloudflare / Medianova | P3 | 1 | Week 5 |  | Not Started | 0
PB-028 | Wave 4 | PB | L1 | CDN Anomaly / Availability Drop — Medianova | Medianova | P3 | 1 | Week 5 |  | Not Started | 0
PB-029 | Wave 4 | PB | L1 | Geo-Blocking Trigger / Suspicious Country of Origin | Cloudflare / FortiGate | P3 | 1 | Week 5 |  | Not Started | 0
PB-030 | Wave 4 | PB | L1/L2 | FortiGate VPN Anomaly (unusual location / brute) | FortiGate | P2 | 2 | Week 4 |  | Not Started | 0
Wave 5 — Email, Insider & User Behavior Playbooks
PB-031 | Wave 5 | PB | L1/L2 | Phishing Email Reported / Detected — FortiMail | FortiMail | P1 | 2 | Week 3 |  | Not Started | 0
PB-032 | Wave 5 | PB | L1/L2 | Malicious Attachment Detected — FortiMail | FortiMail | P1 | 2 | Week 3 |  | Not Started | 0
PB-033 | Wave 5 | PB | L2 | Email Spoofing / BEC (Business Email Compromise) | FortiMail | P2 | 2 | Week 4 |  | Not Started | 0
PB-034 | Wave 5 | PB | L1 | Spam Campaign / Mass Delivery Anomaly | FortiMail | P3 | 1 | Week 5 |  | Not Started | 0
PB-035 | Wave 5 | PB | L2 | Insider Threat — Data Exfiltration Alert (Teramind) | Teramind | P1 | 3 | Week 3 |  | Not Started | 0
PB-036 | Wave 5 | PB | L1 | Acceptable Use Policy Violation — Teramind | Teramind | P2 | 2 | Week 4 |  | Not Started | 0
PB-037 | Wave 5 | PB | L1 | Abnormal Working Hours / After-Hours Access — Teramind | Teramind | P2 | 1 | Week 4 |  | Not Started | 0
PB-038 | Wave 5 | PB | L1/L2 | Credential Stuffing / Account Takeover Attempt | Elastic / Wazuh | P1 | 2 | Week 3 |  | Not Started | 0
PB-039 | Wave 5 | PB | L1/L2 | New Admin Account Created Outside Change Process | Wazuh / Elastic | P2 | 2 | Week 4 |  | Not Started | 0
PB-040 | Wave 5 | PB | L1 | User Account Disabled / Terminated User Still Active | Wazuh / Teramind | P2 | 1 | Week 4 |  | Not Started | 0
TOTALS |  |  |  | 52 |  |  | 104

## KPI Dashboard
SOC DOCUMENTATION KPI DASHBOARD
Metrics pulled live from Master Tracker — update Status and % Complete there
| Total Docs |  |  | SOPs
| 58 |  |  | 12
| Playbooks |  |  | P1 Docs
| 40 |  |  | 26
| Build Days Total |  |  | Approved / Done
| 208 |  |  | 0
STATUS BREAKDOWN BY WAVE
Wave | Category | Total Docs | Not Started | In Progress | Draft Done | Under Review | Approved
Wave 1 | SOPs — Governance Foundation | 12
Wave 2 | Daily Operations Playbooks | 10
Wave 3 | Endpoint & Malware Playbooks | 11
Wave 4 | Network & Perimeter Playbooks | 9
Wave 5 | Email, Insider & User Behavior | 10
QUALITY GATE — All boxes must pass before setting Status = Approved in Master Tracker
[ ] Correct template used — SOP format for SOPs, Playbook format for PBs (never mixed)
[ ] Reviewed by one L1 analyst who has never seen that specific scenario before
[ ] The L1 analyst completed the full task without asking a single clarifying question
[ ] All tools referenced by exact product name (e.g. Elastic, Wazuh — not 'the SIEM')
[ ] Every decision point is an explicit IF / THEN branch (Playbooks only)
[ ] Document Owner and quarterly Review Date are assigned (SOPs only)
[ ] File uploaded to document system and GLPI ticket number logged in Master Tracker

## GLPI Ticket Template
GLPI TICKET TEMPLATE — SOC Document Build Task
TICKET FIELDS
Title | [ID] [Title] — BUILD | PB-016 — Brute Force RDP — BUILD
Category | SOC Documentation | SOC Documentation
Type | Task | Task
Assigned To | Person responsible for this wave | [Analyst Name]
Status — 0% done | Use: New | New
Status — work started | Use: Processing (assigned) | Processing (assigned)
Status — QA passed | Use: Solved (only after QA gate) | Solved
Priority mapping | P1 = Very High ¦ P2 = High ¦ P3 = Medium | Very High / High / Medium
DESCRIPTION BLOCK — paste this into every GLPI ticket description field
Document ID: [SOP-XXX / PB-XXX]
Type: [SOP / Playbook]
Level: [L1 / L2 / Both]
Tool Coverage: [Primary tool(s) — exact product names]
Due Date: [Target week from Master Tracker]
Assigned To: [Name]
Reviewer: [SOC Lead name]
ACCEPTANCE CRITERIA (ALL required before Solved):
[ ] Correct template used (SOP vs Playbook — never mixed)
[ ] Reviewed by L1 analyst unfamiliar with this scenario
[ ] L1 completed task without asking a single question
[ ] All tools named exactly (Elastic, Wazuh — not 'the SIEM')
[ ] IF/THEN decision points present (Playbooks only)
[ ] Owner + Review Date assigned (SOPs only)
[ ] Document uploaded — file location recorded in ticket

## Ownership & Timeline
RECOMMENDED OWNERSHIP SPLIT — 3-PERSON BUILD TEAM
Person | Waves | Focus Area | # Docs | Build Days | Target Done | Actual Done
Person A | Wave 1 + Wave 2 | Governance SOPs + Daily Operations Playbooks | 22 | 46 | Week 4
Person B | Wave 3 + Wave 5 (partial) | Endpoint, Malware, Credential & Insider Threat | 16 | 42 | Week 4
Person C | Wave 4 + Wave 5 (rest) | Network, Perimeter, Email & User Behavior | 14 | 34 | Week 5
WARNING: 104 build-days assigned to 1 person = project failure. Minimum 2 people required. 3 is strongly recommended.
12-WEEK BUILD TIMELINE
Period | Documents Due | Milestone / Goal | Owner
Week 1 | SOP-001/002/003 + PB-001/002/003/004 | Foundation — SOC shift ops + GLPI ticket flow | Person A
Week 2 | SOP-004/005/006 + PB-005..011 + PB-012/016/017 | Incident response + endpoint coverage active | Person A + B
Week 3 | SOP-007/008/009 + PB-009/010/013/014 + PB-022/023 + PB-031/032/035/038 | Full L1 daily coverage across all tools | All
Week 4 | SOP-010/011 + PB-015/018/019/020 + PB-024..030 + PB-033/036/037/039/040 | L2 response coverage complete | Person B + C
Week 5 | SOP-012 + PB-021 + PB-027/028/029 + PB-034 | All 52 documents built | Person B + C
Week 6 | QA review — apply New Hire Test to every document | Quality gate — no document marked Approved without passing | SOC Lead
Week 7+ | Revision cycle based on QA findings | Ongoing — close GLPI tickets only after QA pass | All